## tasks
task_no. | milestone | start_date | end_date | status
1 | Add GlyGen-links to GlyConnect. | anytime | Sept 30
2 | Provide Frederique with flagged/log rows that failed GlyGen-QC (due to position mismatch, glycan type mismatch) for review and to fix/update potential errors | anytime | Review: Sept 15 Fix: Oct 5 | 09/14/2020: File added by rahi. 10/29/2020: 1st round done for Human
3 | Normalize the proteins which were not automatically normalized by the PubTator for the automatic literature mining project. |  |  | 1st round done. 2nd round done.
4 | Get a table with loss/gain of glycosylation data (currently the same rows are flagged due to amino-acid mismatch) [Table will have similar columns biomuta table] |  |  | 10/30/2020: raw data (where the rows which failed QC due to mutation are marked).
5 | Collaboratively decide how to prioritize 100 papers identified by Literature mining,PubMed query, etc | anytime
6 | Include Frederique in Text-mining bi-weekly discussions and get her feedback. |  |  | agreed
7 | Mapping glycan dictionary terms to Ids (GlyConnect Id or GlyTouCan Ac) and adding new terms to dictionary detected from the prioritized from the 100 papers (see point 2.a) | anytime
8 | Verify existing GlyConnect data by marking Fp, Fn on the rows detected from GlyConnect abstracts/full-length papers and provide feedback to Vijay? | anytime | 2020-10-31
9 | Check the disease/cell-line/tissue/impact of glycosylation mentions extracted by the LitMin project. | anytime
10 | Mark Fp,Fn for text extracted from full-length papers (figure-captions, results, etc. | 2020-11-01 | 2020-12-31 | done
11 | Develop a user-friendly submission form to promote glycoscience researchers to submit site-specific glycoconjugate data | 2021-01-01 | 2021-06-30
12 | Develop rules to perform qc and normalization of data to ids. | ?
13 | Implement those rules in addition to existing QC implemented at: https://data.glygen.org/upload | ?
14 | Extend the current two-step process into a form-based system and implement it at GlyGen. | ?

## details_for_tasks
task_no. | milestone | details
1 | Add GlyGen-links to GlyConnect. | Add GlyGen link (glygen.org/protein/%s#glycosylation where %s=uniprotkb canonical accession.) on GlyConnect protein pages (e.g. https://glyconnect.expasy.org/browser/proteins/219) under cross-references. The GlyGen UniProtKB protein to GlyConnect protein id mapping can be found in datasets: 1. https://data.glygen.org/GLYDS000329 [human] 2. https://data.glygen.org/GLYDS000330 [mouse] 3. https://data.glygen.org/GLYDS000331 [rat]
2 | Provide Frederique with flagged/log rows that failed GlyGen-QC (due to position mismatch, glycan type mismatch) for review and to fix/update potential errors | @frederique, do you have a central place where I could upload files for your review? | we use dropbox and google drive with external collaborators. do you prefer a more secure option?
3 | Get “GlyConnect ID to GlyTouCan Ac” mapping file. | GWU will use API for this file.
4 | Get a table with loss/gain of glycosylation data (currently the same rows are flagged due to amino-acid mismatch) [Table will have similar columns biomuta table] | @rahi will discuss the file format with Frederique.
5 | Collaboratively decide how to prioritize 100 papers identified by Literature mining,PubMed query, etc | @discuss it in the LitMin meeting
6 | Include Frederique in Text-mining bi-weekly discussions and get her feedback. | Done
7 | Mapping glycan dictionary terms to Ids (GlyConnect Id or GlyTouCan Ac) and adding new terms to dictionary detected from the prioritized from the 100 papers (see point 2.a) | @discuss it in the LitMin meeting
8 | Verify existing GlyConnect data by marking Fp, Fn on the rows detected from GlyConnect abstracts/full-length papers and provide feedback to Vijay? | @rahi will provide the file when data is ready.
9 | Check the disease/cell-line/tissue/impact of glycosylation mentions extracted by the LitMin project. | discuss it in the LitMin meeting
10 | Mark Fp,Fn for text extracted from full-length papers (figure-captions, results, etc. | @rahi will provide the file when data is ready.
11 | Develop a user-friendly submission form to promote glycoscience researchers to submit site-specific glycoconjugate data | Generate a form based on different file formats GlyGen currently has integrated. @Rahi will provide different file formats.
12 | Develop rules to perform qc and normalization of data to ids. | TBD
13 | Implement those rules in addition to existing QC implemented at: https://data.glygen.org/upload | TBD
14 | Extend the current two-step process into a form-based system and implement it at GlyGen. | TBD