## Sheet1
milestone | start_date | test_date | end_date | GlyGen release (tentative) when the data deliverable will be added to GlyGen | status
1. Develop Glycan list : | 2020-06-01 | 2020-06-15 | 2020-07-31
1.1. Develop the initial system to detect GDS on abstracts of UniCarbKB papers | 2020-06-01 |  | 2020-06-01 |  | done
1.2. Manual verification fp/fn - provide feedback to Vijay | 2020-08-01 | 2020-08-28 | 2020-08-31 |  | in-progress
1.3 Add glycan description strings detected from the software | 2020-08-01 | 2020-09-01 | 2020-09-15 |  | done
1.4. Add ‘Term in sentence’, PMID, PMID count. | 2020-08-01 | 2020-09-01 | 2020-09-15 |  | done
1.5. Add definition, synonyms manually and utilize them to explore normalization of the GDS using GNome. Possibly ask other team experts to contribute. Add reviewed sets to GlyGen data.org | 2020-08-01 | 2020-09-10 | 2020-09-15 | 2020-09-24 | in-progress
2. Run the current software on GlyGen papers (from UniCarbKB, GlyConnect, UniProtKB, etc). for Protein+site for Abstracts | 2020-09-15 | 2020-10-01 | 2020-11-15 |  | done-entire GlyGen set
2.1. Run system set-wise on abstract and produce output for UniCarbKB and GlyConnect papers | 2020-09-15 | 2020-10-01 | 2020-10-15 |  | done-uckb+entire glygen set
2.2. Manual inspection of output | 2020-09-15 | 2020-10-01 | 2020-10-15 |  | done-uckb+entire glygen set
2.3. Provide Fp and Fn to Vijay and team | 2020-09-15 | 2020-10-01 | 2020-10-15 |  | done-uckb+entire glygen set
2.4. Pass rows through automatic QC | 2020-09-15 | 2020-10-01 | 2020-10-15
2.5. Provide passed (manual and automatic) rows to front-end | 2020-09-15 | 2020-10-01 | 2020-10-15
2.6. Add Literature mining as an additional evidence badge for the detected sites and link to Vijay’s website | 2020-09-15 | 2020-10-01 | 2020-10-15 | 2020-10-22
2.7. Generate statistics (set-wise) | 2020-10-15 | 2020-10-15 | 2020-10-15 | 2020-10-22
2.8. Evaluate the scope of automatic vs manual work. | 2020-10-15 | 2020-10-15 | 2020-10-15
2.9. Present those statistics other groups and get input | 2020-10-15 | 2020-10-15 | 2020-10-15
2.10. Vijay to incorporate manual feedback (fn/fp) to improve the system. | 2020-09-20 | 2020-10-15 | 2020-10-31
2.11. Run the refined system on the entire GlyGen set (total 1324 papers) | 2020-10-31 | 2020-10-31 | 2020-10-31
2.12. Repeat the pipeline 2.2-2.6 to provide passed rows to the front-end. | 2020-10-31 | 2020-11-01 | 2020-12-07 | 2020-12-24
2.13. Refine the system for glycan description strings (abstract-only) based on the feedback on 1.1 | 2020-11-15 |  | 2020-12-07
2.14. Run it on the GlyGen paper (1324) set. | 2020-10-31 | 2020-11-01 | 2020-11-15
2.15. Provide the raw list of detected glycan strings. | 2020-10-31 | 2020-11-01 | 2020-11-15 | 2020-03-12
3. Move to Full-length (GlyGen set + open access)- GlyGen set | 2020-11-15 | 2021-02-05 | 2021-03-15
3.1. Evaluate distribution of information in different papers (old, new) | 2020-11-15 | 2021-02-05 | 2021-03-15
3.2. Run the abstract-based system on the results, subsection, figure captions. | 2020-11-15 | 2021-02-05 | 2021-03-15
3.3. Manual check- fp, fn | 2020-11-15 | 2021-02-05 | 2021-03-15
3.4. Refine system based on feedback. | 2020-11-15 | 2021-02-05 | 2021-03-15
3.5. Generate statistics. | 2020-11-15 | 2021-02-05 | 2021-03-15
3.6. Develop a mockup for GlyGen UI data display and push the data to front-end | 2020-11-15 | 2021-02-05 | 2021-03-15 | 2021-04-08
4. Update Glycan list. | 2020-11-15 | 2021-01-05 | 2021-03-01
4.1. Add new glycan description strings from 2.15 detected from the software. | 2020-11-15 | 2021-01-05 | 2021-03-01
4.2. Add ‘Term in sentence’, PMID, PMID count automatically. | 2020-11-15 | 2021-01-05 | 2021-03-01
4.3. Add definition, synonyms manually and utilize them to explore normalization of the GDS using GNome. Possibly ask other team experts to contribute. | 2020-11-15 | 2021-02-05 | 2021-03-01
4.5 Apply the GDS dectection using manually refined glycan terms to entrire PubMed abstracts and report PMIDs.
5. Association of GDS to protein-site: | 2021-03-01 | 2021-03-15 | 2020-04-30
5.1. Develop the initial system on abstract only | 2021-03-01 | 2021-03-15 | 2020-04-30
5.2. Manual verification fp/fn - provide feedback | 2021-03-01 | 2021-03-15 | 2020-04-30
5.3. Refine the system | 2021-03-01 | 2021-03-15 | 2020-04-30
5.4. Run it on the combined set (GlyGen paper (1324) set + outside GlyGen papers) | 2021-03-01 | 2021-03-15 | 2020-04-30
5.5. Generate mockup for front-end display and push to production | 2021-03-01 | 2021-03-15 | 2020-04-30 | 2021-05-13
6. Extract mentions: | 2020-04-30 | 2021-05-15 | 2021-05-30
6.1. Detect mention(s) of disease and cell-type/tissue in abstracts. | 2020-04-30 | 2021-05-15 | 2021-05-30
6.2. Impact of glycosylation | 2020-04-30 | 2021-05-15 | 2021-05-30
6.3. Run system developed for general detection of impact of process/entity on another process/entity on abstracts (GlyGen-set) | 2020-04-30 | 2021-05-15 | 2021-05-30
6.4. System will identify potentially relevant phrases which will be manually checked. | 2020-04-30 | 2021-05-15 | 2021-05-30 | 2021-06-17
7. Generalizing the system: | 2021-05-30 | 2021-06-15 | 2021-06-30
7.1. Run on the wider range of abstracts/full-length | 2021-05-30 | 2021-06-15 | 2021-06-30
7.2. Develop a query as many abstracts as possible | 2021-05-30 | 2021-06-15 | 2021-06-30
7.3. Run the system on those abstracts | 2021-05-30 | 2021-06-15 | 2021-06-30 | 2021-07-08
7.4. How many are OA and refine the query to prioritize the papers for a full-length system. | 2021-05-30 | 2021-06-15 | 2021-06-30 | 2021-07-08
7.5. Evaluate migrating Vijay’s website to iTextMine/GWU server. | 2021-05-30 | 2021-06-15 | 2021-06-30
7.6. Dockerize the system with detailed documentation. | 2021-05-30 | 2021-06-15 | 2021-06-30 | 2021-07-08