Discussions/Action-items:

- Run the current software on GlyGen papers (from UniCarbKB, GlyConnect, UniProtKB, etc).

  - Abstracts only - Protein + Site detection:

    - Preliminary system development: (set-wise*)

      - Run system set-wise and produce output. [UC/GC-09/15]

      - Manual inspection of output

      - Provide Fp and Fn to Vijay and team

      - Pass rows through automatic QC

      - Provide passed (manual and automatic) rows to front-end:

        - Add Literature mining as an additional evidence badge for the detected sites and link to Vijay’s website (e.g. link). [UC/GC: 10/15]

      - Generate statistics (set-wise):

        - % for every step:

          - protein-site detected by LitMin [UC/GC:10/15]

          - Evaluate the scope of automatic vs manual work [UC/GC:10/15]

        - Present those statistics other groups and get input [data meeting after 10/15]

      - Vijay to incorporate manual feedback (fn/fp) to improve the system.

    - Refined system

      - Run the refined system on the GlyGen set (1324 papers) [10/31]

      - Repeat the pipeline to provide passed rows to the front-end.  [12/07]

  - Abstracts only: glycan description recognition

    - Develop the initial system

      - Manual verification fp/fn - provide feedback on 100 abstracts [08/31]

    - Refine the system

      - Run it on the GlyGen paper (1324) set [11/15]

    - Provide the raw list of detected glycan strings [11/15]

- Move to Full-length (GlyGen set + open access) : [03/15/2021]

  - Evaluate distribution of information in different papers (old, new)

  - Run the abstract-based system on the results, subsection, figure captions.

  - Manual check- fp, fn

  - Refine system based on feedback.

  - Generate statistics.

  - Develop a mockup for GlyGen UI data display.

- Develop Glycan list : [03/01/2021]

  - Add glycan description strings detected from the software. [UC-09/15]

  - Add ‘Term in sentence’, PMID, PMID count automatically. [UC-09/15]

  - Add definition, synonyms manually and utilize them to explore normalization of the GDS using GNome. Possibly ask other team experts to contribute. [UC-09/15]

- Association of GDS to protein-site: Abstracts only [04/30/2021]

  - Develop the initial system

    - Manual verification fp/fn - provide feedback

  - Refine the system

    - Run it on the GlyGen paper (1324) set

  - Front-End:

    - Generate mockup for front-end display

- Extract mentions: [05/30/2021]

  - Detect mention(s) of disease and cell-type/tissue in abstracts.

  - Impact of glycosylation

    - Run system developed for general detection of impact of process/entity on another process/entity on abstracts (GlyGen-set)

    - System will identify potentially relevant phrases which will be manually checked.

- Generalizing the system:[6/30/2021]

  - Run on the wider range of abstracts/full-length

    - Develop a query as many abstracts as possible

    - Run the system on those abstracts

    - How many are OA and refine the query to prioritize the papers for a full-length system.

  - Evaluate migrating Vijay’s website to iTextMine/GWU server.

  - Dockerize the system

*Set:

- UniCarbKB

- GlyConnect

- UniProtKB

- Others

| Table 1: |  |  |
| --- | --- | --- |
| Step | Issue | solution(s)? |
| Extract papers based on query | Not a efficient query to capture glycosylation_site information Only 20-30% of the extracted papers actually have some mention of glycosylation or site. | Combine two or more queries? Use the query from Stephanie for O-GlcNAc data (758) ((O-GlcNAc[Title/Abstract]) OR O-GlcNAcylated[Title/Abstract] OR O-GlcNAcylation[Title/Abstract]) NOT review[Publication Type] NOT systematic review[Publication Type]) |
| Extract data from abstracts | Abstracts may not mention data | Numbers can improve once we move to full-length. |
| Protein name to UniProtKB normalization | PubTator can only normalize 70-80% of the protein names | Create our own dictionary. |
| Manual QC | Detection of false positives (roughly 10%) And false negatives (20%) | Report back to Vijay to fix issues. |
| Automatic QC | Site validation failing (>50%) | Manual alignment |